## backlog-epics
Epic | Epic # | Item | Description | Priority | Complexity | Source | Status
Quick Wins | 1 | Regenerate Plan guidance modal | Replace confirm() with Dialog + textarea for guidance text fed to AI | High | Small | ENH #15 | Pending
Quick Wins | 1 | Default meal skip setting | Allow setting a default meal type to skip (e.g. always skip breakfast) | High | Small | SS 2026-03-27 | Pending
Quick Wins | 1 | Meal name truncation | Ensure full recipe names displayed on plan output page ‚Äî never cut off | Medium | Small | SS 2026-03-27 | Pending
Dynamic Meals | 2 | MealComponent Prisma model | New model: { id householdId category:PROTEIN¦VEGGIE¦STARCH¦SAUCE name prepMethods[] defaultCookTime? } | High | Medium | ENH B2 | Pending
Dynamic Meals | 2 | isDynamic flag on PlannedMeal | Distinguish dynamic meals from recipe-based meals in DB schema | High | Small | ENH B2 | Pending
Dynamic Meals | 2 | CRUD API routes | Create /api/settings/meal-components endpoints | High | Medium | ENH B2 | Pending
Dynamic Meals | 2 | Management UI page | /meal-components page with category tabs (Protein Veggie Starch Sauce) | High | Medium | ENH B2 | Pending
Dynamic Meals | 2 | AI prompt update | Include component library + instructions for composing dynamic meals | High | Medium | ENH B2 | Pending
Dynamic Meals | 2 | Grocery generation for dynamic meals | Look up each component's typical ingredients for grocery list | Medium | Medium | ENH B2 | Pending
Dynamic Meals | 2 | Sidebar nav entry | Add meal components link to navigation | Low | Small | ENH B2 | Pending
Grocery List QoL | 3 | Manual grocery item addition | Simple text input + section picker to add custom items to grocery list | High | Small | ENH B3 | Pending
Grocery List QoL | 3 | Hide permanently ‚Üí PantryStaple | Button on grocery items that adds ingredient to PantryStaple with confirmation | High | Small | ENH B4 | Pending
Grocery List QoL | 3 | Recurring grocery buys | New model + settings page for items always added to grocery list; checkbox on generation | Medium | Medium | ENH B5 | Pending
Planning Refinements | 4 | Named planning guidelines | Save multiple guideline sets with names; select when generating (assess if presets cover this) | Medium | Medium | SS 2026-03-28 | Pending
Planning Refinements | 4 | Max servings scaling | Auto-halve recipes >8 servings for smaller households. Only 1 recipe exceeds 8 currently | Low | Small | ENH B1 | Pending
Planning Refinements | 4 | Bulk-add missing cook times | UI to identify and batch-update the 22 recipes missing time data | Medium | Small | ENH B9 | Pending
Auth & Login | 5 | Magic link auth (NextAuth) | Replace mock auth with NextAuth magic link login for you and your wife | High | Medium | P1.0-K / MVP | Pending
Auth & Login | 5 | Approved email allowlist | Simple config of 2 approved email addresses ‚Äî no signup flow needed | Medium | Small | Interview | Pending
Auth & Login | 5 | Shared household data | Both users see same recipes / plans / settings (already scoped by householdId) | Low | Small | P1.0-K | Pending
Google Calendar | 6 | Calendar event creation | Create events for each planned meal with name / recipe link / meal type / servings | High | Medium | P1.1 | Pending
Google Calendar | 6 | Configurable meal time events | Default times (8am/12pm/6pm) with user-adjustable settings; option for all-day events | Medium | Small | P1.1 | Pending
Google Calendar | 6 | Event update on plan edit | When meal plan changes update/delete corresponding calendar events | Medium | Medium | P1.1 | Pending
Google Calendar | 6 | Calendar selection | User selects which Google Calendar to use; support shared calendars | Low | Small | P1.1 | Pending
Google Calendar | 6 | Store event IDs | Link PlannedMeal records to Google Calendar event IDs for sync | Medium | Small | P1.1 | Pending
Error & Stability | 7 | Application-wide error audit | Investigate all routes for errors and latency beyond known fixes | Medium | Medium | ENH #16 | Pending
Someday / Maybe | 8 | Responsive web design | Mobile-friendly layouts for all pages | ‚Äî | Large | P2 / ENH B8 | Parked
Someday / Maybe | 8 | Progressive Web App | Offline support / installable / push notifications | ‚Äî | Large | P2 | Parked
Someday / Maybe | 8 | Recipe cooking timer | Track actual cook times during meal prep (needs mobile/PWA) | ‚Äî | Medium | ENH B7 | Parked
Someday / Maybe | 8 | Web recipe search | Search the web for new recipes via AI | ‚Äî | Large | P2 | Parked
Someday / Maybe | 8 | Ingredient-based discovery | "What can I make with what I have?" input + AI suggestions | ‚Äî | Large | P2 | Parked
Someday / Maybe | 8 | Calorie counting/estimation | Nutritional info tracking per meal | ‚Äî | Large | P2 | Cut
Someday / Maybe | 8 | Daily/weekly nutritional summaries | Aggregated nutrition data across plans | ‚Äî | Large | P2 | Cut
Someday / Maybe | 8 | Meal prep time blocking | Block prep time on calendar before meal events | ‚Äî | Medium | P2 | Parked
Someday / Maybe | 8 | Reminder notifications | Push/email reminders for meal prep | ‚Äî | Medium | P2 | Parked
Someday / Maybe | 8 | Bidirectional calendar sync | Changes in Google Calendar reflected in app | ‚Äî | Large | P2 | Parked
Someday / Maybe | 8 | Shopping trip scheduling | Calendar events for grocery runs | ‚Äî | Small | P2 | Parked
Someday / Maybe | 8 | Recipe scaling | Auto-scale recipes up/down with unit conversions | ‚Äî | Medium | P2 | Parked
Someday / Maybe | 8 | Inventory/pantry tracking | Track what's in the pantry; suggest meals for expiring ingredients | ‚Äî | Large | P2 | Parked
Someday / Maybe | 8 | AI-discovered recipe saving | When AI finds recipes online allow saving to recipe library | ‚Äî | Medium | P1.0-F.2 | Cut
Someday / Maybe | 8 | Meal day-swap (drag) | Drag or swap meals between days (current: swap recipe only not slot) | ‚Äî | Medium | P1.0-I.1 | Cut